# Transitioning a Mass Care Leadership Role Task Sheet

Description: Provides detailed guidance for how to support the transition between DRO Headquarters Mass Care leaders on a DRO

Typically performed by: HQ Mass Care Chiefs and Mass Care activity managers

Supporting on the task: AD of Operations and Workforce section

## Considerations

Leadership transitions are normal during disaster relief operations (DROs).

Most assignments last for about 2 to 3 weeks. Regional responses may result in shorter or longer assignments.

Leadership positions often take longer for the Workforce section to fill, so plan at least 5 days for the planned leadership transition.

## What To Do

- Determine the out-processing date of the Mass Care leader.

The out-processing date is the last work day of a deployed worker and can be found on the Daily Staffing Roster (see Ensuring the Mass Care Team has access to Situational Awareness Reports Task Sheet for information on how to get this report) .

- Submit an approved staff request to backfill the position with a travel date at least 24 hours before the day the replacement is needed.

- Review the Arrival Roster for the name of the replacement (see Ensuring the Mass Care Team has access to Situational Awareness Reports Task Sheet for information on how to get this report) .

Ensure the incoming worker has access to all necessary information, including documents, Teams sites, shared documents and WebEOC as appropriate for their role.

The leaving Mass Care leader is responsible for communicating the following:

Service delivery sites.

Pending missions or issues.

- Current staff rosters and anticipated needs.

- What phase (initiating, stabilization, or closing) the DRO is currently operating in.

## Links/Related Information

- Any Workforce information about worker transitions

- DRO Staff Request Form

- Ensuring the Mass Care Team has access to Situational Awareness Reports Task Sheet