Daily Tactics Planning (completing the 215s) & Communicating Mass Care Needs to DRO Leaders Task Sheet

Description: Provides guidance on daily tactics planning and communicating mass care needs to operational leadership.

Typically performed by: Mass Care activity managers & HQ Mass Care Chiefs

Supporting on the task: AD of Operations, Information & Planning section, and External Relations section

## Considerations

- Each disaster relief operation (DRO) follows the standard Incident Command System (ICS) incident planning process.

- The incident planning process is designed to identify critical pathways, resource requirements, and roadblocks for each mass care delivery site. Successful application of the planning process requires close collaboration with the Information & Planning section and discipline to keep to the deadlines and meetings required by the process.

- Tactics and work assignments are updated during the operational period (normally 24 hours) using an Operational Planning Worksheet (215) and presented in the Tactics meeting.

- It’s equally important that Mass Care leaders are deliberate in communicating Mass Care leaders' needs or constraints to DRO Leaders. The planning process gives Mass Care leaders the framework to effectively communicate these needs.

## What To Do

### Operational Tactics & Preparing the Operational Planning Worksheet (215)

- Review the incident objectives in the Incident Action Plan (IAP) and/or obtain incident objectives from the AD of Operations.

- Understand the current situation

- Use WebEOC and other information sources (including your supervisor) to figure out pending requests, current service sites/delivery, projected requests, etc.

- Pull up your Mass Care Planning Assumptions, functional plans, and information from DRO leadership to determine the Mass Care service delivery requirements.

- An example: Leadership has communicated the need to fulfill all pending shelter requests as soon as possible. Currently there are 15 shelters missions in the WebEOC mission tracker that we must resource and open. We then need 15 shelter teams to support these 15 shelter missions.

- Open the Operational Planning Worksheet (215)

- Complete the Operational Planning Worksheet (215) using the instructions in the sheet. Please note this is the plan for the next operational period, not the current one.

  - Resource Identifier is where you place the worksite (ie. a Kitchen site, DES route, shelter site etc.). This is also where you identify teams that are assigned to a general area and will complete critical missions that come up during the operational period (i.e.. Shelter Team #1 is on-standby to activate a shelter in Orleans Parish, Address TBD).

  - When the DR is still initiating and the service delivery is still not stabilized, it is a best practice to keep some teams on alert to fulfill urgent requests that come in.

    - For example, let’s say you have 10 ERVs at Kitchen #1, you may have 7 defined feeding routes. You should consider having 3 ERVs on alert to handle urgent missions. If no urgent missions come, you can work with Information and Planning to come up with alternative routes for the ERV to do seek and serve if no missions come up.

- Review the completed Operational Planning Worksheet (215) make note of:

  - Resource shortfalls

  - Resource surpluses

  - Resources on alert/stand-by

  - Missions or tasks that cannot be fulfilled during this operational period

- Ensure 215s are ready to be reviewed at the 1300 Tactics Meeting.

  - It is imperative that the 215 is complete and ready before the tactics meeting. If that’s not possible this must be communicated to your supervisor.

- If needed, adjust 215s as the situation evolves. It is imperative that any changes be communicated to your supervisor and ultimately the AD of Operations as well as other key stakeholders.

### Identifying Critical Pathways, resource requirements, and Roadblocks

- Assemble your team to review the 215 before the tactics meeting to determine what shortfalls or other considerations may/will impact your ability to execute the plan.

  - Considerations may include (but are not limited to):

    - Resource shortfalls

    - Transportation

    - Traffic/ Road accessibility

    - Travel Time/ location of resources

    - Curfews

- Make note of these items and be prepared to discuss during the Tactics Meeting. If the Mass Care Chief is representing you in the meeting, brief them on these items before the tactics meeting.

### Conveying Critical Pathways and Roadblocks

- Once you have a good understanding of critical pathways and roadblocks, convey the information to operational leadership (this is typically done in the Tactics Meeting).

  - Making sure to include:

    - The roadblock/ critical pathway

    - What is needed to overcome roadblocks

    - Proposed alternatives or options (if possible)

    - Impacts on service delivery

- It is important to use precise language when conveying these. Instead of being vague and saying, “We can’t do this,” say “We need 20 more ERV drivers to achieve this task.”

## Links / Related Information

- Operational Planning Worksheet